| # ClubSport Event Timing Schedule |  |  |
| --- | --- | --- |
| Notes to Organisers: This document is designed to supplement the Event Checklists (CS 001 and CS 002) Organiser should completed the “By when” column noting either the latest date or time applicable to the item concerned and then tick the box when task has been completed. |  |  |
| ## Part A – Pre Event |  |  |
| Tick Box | ### Task to be completed | ### By when |
|  | Visit residents to gain support and respond to concerns (required if event is to be held on a closed road) |  |
|  | Prepare Supplementary Regulations / Notification of Event to go into Club Bulletin or Magazine |  |
|  | Apply for road closure (if applicable) |  |
|  | Send first letter to residents (if applicable) |  |
|  | Prepare Event Safety Plan |  |
|  | Receive written permission for use of the venue or road |  |
|  | Apply for Event Permit |  |
|  | Send second letter to residents (if applicable) |  |
|  | Arrange for all event officials and marshals |  |
|  | Arrange for all equipment to be on site |  |
| ## Part B – On Event |  |  |
|  | Documentation completed |  |
|  | Scrutineering completed |  |
|  | Road closure marshals briefed and issued with appropriate paperwork. |  |
|  | Road closure signs and barriers in place |  |
|  | Course marshals briefed |  |
|  | Competitors briefing completed |  |
|  | New competitors briefing completed |  |
|  | Passenger briefings completed |  |
|  | Course marshals and markers in place |  |
|  | Spectator areas set up as per Safety Plan |  |
|  | Clearance Certificate prepared and signed |  |
|  | Course ready for Steward or Steward Safety Officers Inspection |  |
|  | First run to commence |  |
| ## Part C – Post Event |  |  |
|  | Last run concluded and course cleared |  |
|  | Road closure signs and barriers dismantled |  |
|  | Venue cleared of all equipment and rubbish removed |  |
|  | Marshals and Officials thanked |  |
|  | Debrief with Steward or Steward Safety Officer on site. |  |
|  | Participation levy form completed and sent to MotorSport NZ |  |
|  | Letters of thanks sent to venue owner and effected residents. |  |
|  | Organise event debrief |  |